## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
77147 | 15/YH/0233 | 179038 | NHS Permission | CLEARCarotid | 2015-06-22 | 2015-07-07 | Yes | 2015-08-03 | 15 | 27 | 42 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77148 | 14/YH/0076 | 141623 | NHS Permission | BALANCED | 2015-09-03 | 2015-09-03 | Yes | 2015-09-14 | 0 | 11 | 11 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77149 | 14/NI/1120 | 149397 | NHS Permission | EDNA | 2015-08-04 | 2015-08-17 | Yes | 2015-08-25 | 13 | 8 | 21 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77150 | 14/SC/1219b | 159391 | NHS Permission | AIRWAYS 2 - Scarborough | 2015-08-14 | 2015-08-14 | No |  | 0 |  |  | No | [6 empty] | Please Select... | [10 empty] | Y | Patients can only be recuited following admission by ambulance and ICU survival. Potential recruits are rare and we have no agreed local target with Sponsor. The study is open until July 2-17. Just one potential patient has presented in Scarborough who died. | Neither
77152 | 13/SS/0081 | 128254 | NHS Permission | TWICS | 2015-07-22 | 2015-08-25 | No |  | 34 |  |  | No | [6 empty] | Please Select... | [7 empty] | Y |  |  | Y | Recruitment proving challenging as patients existing medication is a factor as well as other medical problems due to the drug involved. Currently looking to open local PIC sites (GP practices) to aid recruitment. | NHS Provider
77153 | 14/EM/1173 | 162392 | NHS Permission | HI-Light Vitiligo Trial | 2015-07-09 | 2015-07-31 | Yes | 2015-08-18 | 22 | 18 | 40 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77154 | 12/WM/0335 | 97743 | NHS Permission | OCS-Care | 2015-09-02 | 2015-09-02 | Yes | 2015-09-24 | 0 | 22 | 22 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77155 | 15/LO/0992 | 173319 | NHS Permission | Proactive Health Coaching in the English NHS | 2015-07-31 | 2015-07-31 | Yes | 2015-08-17 | 0 | 17 | 17 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77156 | 14/WA/1075 | 150715 | NHS Permission | Headpost | 2015-09-22 | 2015-09-22 | Yes | 2015-09-28 | 0 | 6 | 6 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77157 | 14/LO/0203 | 137863 | NHS Permission | CLARITY | 2015-06-10 | 2015-06-11 | Yes | 2015-07-03 | 1 | 22 | 23 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77158 | 13/YH/0229 | 125373 | NHS Permission | GO2 Version 1.0 - Scarborough | 2015-06-09 | 2015-07-01 | Yes | 2015-08-06 | 22 | 36 | 58 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77159 | 14/SC/1425 | 159287 | NHS Permission | SPECTRI | 2015-06-24 | 2015-07-08 | Yes | 2015-08-28 | 14 | 51 | 65 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77160 | 15/YH/0235 | 168009 | NHS Permission | IMPACCT | 2015-10-13 | 2015-10-13 | Yes | 2015-11-09 | 0 | 27 | 27 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77161 | 15/SC/0287 | 173772 | NHS Permission | Provision of Psychological support to People in Intensive Care (v1.0) - POPPI | 2015-10-16 | 2015-10-16 | Yes | 2015-11-06 | 0 | 21 | 21 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77162 | 14/SC/0171 | 120104 | NHS Permission | Add-Aspirin | 2015-11-11 | 2015-12-29 | Yes | 2016-03-07 | 48 | 69 | 117 | No | [6 empty] | Please Select... | [6 empty] | Y | Y |  |  |  | No eligible participants due to eligibility criteria | NHS Provider
77163 | 13/EM/0348 | 122371 | NHS Permission | Monoprost compared to Lumigan in POA glaucoma/ocular hypertension | 2015-06-16 | 2015-11-02 | No |  | 139 |  |  | No | [6 empty] | Please Select... |  |  |  |  | Y | Y | [5 empty] | Delay in green lighting study locally mainly caused by delayed receipt of drug from sponsor. Also a delay in getting confirmation of a second investigator at site. | Both
77164 | 14/NW/0277 | 121660 | NHS Permission | BreatheMOR-HF: Morphine for breathlessness in heart failure | 2015-11-11 | 2015-11-27 | Yes | 2016-02-04 | 16 | 69 | 85 | No | [6 empty] | Please Select... | [7 empty] | Y |  |  |  | Participants failed to recruit | NHS Provider
77165 | 10/H0802/46 | 52863 | NHS Permission | REVIVED-BCIS2 Version 1.0 | 2015-11-10 | 2015-11-12 | Yes | 2016-08-08 | 2 | 270 | 272 | No | [6 empty] | Please Select... | [6 empty] | Y | Y |  |  |  | Eligibility criteria | NHS Provider
79200 | 14/YH/1259 | 163195 | NHS Permission | ALPHA | 2016-01-22 | 2016-02-19 | Yes | 2016-05-18 | 28 | 99 | 128 | No | [6 empty] | Please Select... | [6 empty] | Y | Y |  |  |  | Eligibility criteria | Please Select...
79201 | 15/LO/1166 | 178877 | NHS Permission | HARRIER RTH 258 | 2016-01-20 | 2016-02-19 | No |  | 30 |  |  | No | [6 empty] | Please Select... | [11 empty] | Sponsor met global target and closed study | Sponsor
79203 | 15/EE/00/10 | 138590 | NHS Permission | PITCHES | 2016-03-21 | 2016-03-31 | Yes | 2016-07-08 | 10 | 84 | 94 | No | [6 empty] | Please Select... | [7 empty] | Y |  |  |  | Eligible patients declined | NHS Provider
23788 | 14/WM/0083 | 125950 | NHS Permission | LORIS | 2016-04-07 | 2016-04-19 | No |  | 17 |  |  | No | [14 empty] | Y |  |  |  | Eligible patients declined. | NHS Provider
23587 | 14/SC/0295 | 154130 | NHS Permission | IMPALA | 2016-03-31 | 2016-04-29 | No |  | 29 |  |  | No | [13 empty] | Y |  |  |  |  | No eligible patients found. Very limited eligibility criteria | NHS Provider
47049 | 15/WA/0106 | 167739 | NHS Permission | PROBESE | 2016-03-29 | 2016-04-05 | Yes | 2016-04-22 | 7 | 17 | 24 | Yes
31083 | 15/LO/1015 | 182526 | NHS Permission | AQUA | 2016-03-24 | 2016-04-14 | No |  | 21 |  |  | No | [14 empty] | Y |  |  |  | Eligible patients declined. | NHS provider
50794 | 15/LO/1595 | 183040 | NHS Permission | PRISM | 2016-03-29 | 2016-05-09 | Yes | 2016-06-06 | 41 | 28 | 70 | Yes
46985 | 15/YH/0467 | 191055 | NHS Permission | A Study of GSK3196165 in Hand Osteoarthritis - MUSC 4867 | 2016-03-10 | 2016-04-01 | Yes | 2016-10-06 | 22 | 206 | 229 | No | [14 empty] | Y |  |  |  | Eligibility criteria | NHS provider
65106 | 16/LO/0212 | 186869 | NHS Permission | CREATE | 2016-06-24 | 2016-06-24 | Yes | 2016-08-16 | 0 | 53 | 53 | Yes |  | 2016-01-15 | 2016-01-15 | 2016-06-23 | 2016-03-11 | 2016-03-11 |  | 2016-06-24
27955 | 14/EE/1293 | 164389 | NHS Permission | C-STITCH | 2016-07-01 | 2016-08-15 | Yes | 2016-08-16 | 39 | 1 | 40 | Yes |  | 2016-04-19 | 2016-04-19 | 2016-08-10 | 2016-08-15 | 2016-08-15 |  | 2016-08-16
23102 | 13/NE/0339 | 131556 | NHS Permission | GOT-IT | 2016-07-05 | 2016-08-18 | Yes | 2016-09-06 | 45 | 20 | 65 | Yes |  | 2016-04-19 | 2016-04-19 | 2016-06-24 | 2016-08-16 | 2016-07-27 |  | 2016-07-27
73020 | 16/YH/0186 | 200765 | C&C | RENA 5453 | 2016-08-02 | 2016-09-21 | No | 2017-01-18 | 51 |  |  | No |  | 2016-03-23 | 2016-03-23 | 2016-07-28 | 2016-09-21 | 2016-09-21 |  | 2016-09-21 | [6 empty] | Y |  |  |  | Eligible patients declined | NHS Provider
11431 | 12/WM/0010 | 90943 | C&C | PRIDE | 2016-10-04 | 2016-11-01 | Yes | 2016-11-01 | 29 | 0 | 29 | Yes |  | 2016-09-15 | 2016-10-04 | 2016-08-05 | 2016-11-01 | 2016-11-01 |  | 2016-11-01
50388 | 16/LO/0334 | 193988 | C&C | GS-US-296-1080 | 2016-04-27 | 2016-11-11 | No |  | 199 |  |  | No |  | 2015-07-21 | 2015-07-21 | 2016-04-26 | 2016-11-11 | 2016-11-11 |  | 2016-11-11 |  |  |  |  | Y |  |  | Y |  |  | A number of staff within the Oncology team left post at the start of setup. There were then some furthger delays with costing negotiations | Sponsor & NHS Provider
20153 | 13/WA/0205 | 127379 | C&C | AML 18 | 2016-10-03 | 2016-11-15 | Yes | 2016-11-17 | 45 | 2 | 47 | Yes |  | 2015-07-02 | 2015-07-02 | 2016-08-01 | 2016-11-15 | 2016-11-15
72813 | 16/SC/0351 | 205115 | NHS Permission | COTEZO | 2016-11-23 | 2016-12-05 | No |  | 12 |  |  | Yes | 2016-09-05 | 2016-02-29 | 2016-05-10 | 2016-10-05 | 2016-05-10 | 2016-05-10 |  | 2016-12-05 |  |  | Y |  |  |  |  | Y |  | Y | Closure of Aseptics department In Scarborough meant extra SOPs and testing was required by the pharmacy team to ensure the drug could travel between sites. There were a number of issues of contracting. Due to competative recruitment Europe overrecruited and as a result Scarbrough lost their recruitment slots. | Sponsor & NHS Provider
21394 | 14/WA/1056 | 154468 | C&C | AML19 | 2016-10-25 | 2016-12-29 | No |  | 66 |  |  | No | 2016-07-15 | 2016-07-15 | 2016-07-15 | 2016-06-15 | 2016-12-31 | 2016-12-29 |  | 2016-12-30 |  |  |  | Y |  |  | Y |  |  |  | Sponsor delays with delivering IMP. No eligible patients availble within window | Sponsor & NHS Provider
19930 | 14/ES/1004 | 101577 | C&C | PRE-EMPT | 2017-01-11 | 2017-01-12 | No |  | 1 |  |  | No | 2016-10-04 | 2016-10-04 | 2017-01-11 | 2016-09-29 | 2016-01-12 | 2016-01-12 |  | 2016-01-12 | [5 empty] | Y |  |  |  |  | No eligible patient seen during window.
65388 | 16/WA/0069 | 198007 | C&C | VICI | 2016-12-06 | 2017-01-18 | No |  | 44 |  |  | No | 2016-06-23 | 2016-06-23 | 2016-12-06 | 2016-07-21 | 2017-02-02 | 2017-02-02 |  | 2017-02-02 |  |  |  | Y |  | Y |  |  |  |  | Sponsor delayed in approving photography signatures. Only potentially eligible patient within window failed screening | Sponsor & NHS Provider
20563 | 13/EE/0397 | 132094 | C&C | NIMRAD | 2017-02-24 | 2017-02-28 | No |  | 0 |  |  | N/A | 2016-03-10 | 2016-03-10 | 2016-10-21 | 2016-06-15 | 2017-03-08 | 2017-02-28 |  | 2017-03-09 | [10 empty] | Window still open as at end of Q4 - End of April
30186 | 14/WM/1170 | 161147 | C&C | COMPARE | 2017-01-11 | 2017-03-24 | No |  | 73 |  |  | No | 2016-08-24 | 2016-08-24 | 2017-01-11 | 2016-05-23 | 2017-03-31 | 2017-03-24 |  | 2017-03-31 |  |  |  | Y |  |  |  | Y |  | Y | Delay in from 6th of Jan to 24th Feb in receiving contracts back from Sponsor. The further delays by locla pharmacy arrangements. | Sponsor & NHS Provider
89527 | 14/NE/1180 | 145170 | C&C | UK GRIS | 2017-01-16 | 2017-03-20 | Yes | 2017-03-27 | 63 | 7 | 70 | Yes | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-01-16 | 2017-03-14 | 2014-03-14 |  | 2017-03-20

## Sheet2
2016-10-04
2016-10-05
2016-10-06
2016-10-07
2016-10-08
2016-10-09
2016-10-10
2016-10-11
2016-10-12
2016-10-13
2016-10-14
2016-10-15
2016-10-16
2016-10-17
2016-10-18
2016-10-19
2016-10-20
2016-10-21
2016-10-22
2016-10-23
2016-10-24
2016-10-25
2016-10-26
2016-10-27
2016-10-28
2016-10-29
2016-10-30
2016-10-31
2016-11-01
2016-11-02
2016-11-03