## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of Receipt of Valid Research Application | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Duration between VRA and First Patient | Benchmark Met | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
77136 | 14/WM/1263 | 165806 | NHS Permission | Ektotherix | 2015-04-08 | 2015-04-08 | Yes | 2015-04-30 | 0 | 22 | 22 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77137 | 14/YH/1170 | 140209 | NHS Permission | CLEARNOF - Scarborough | 2015-04-13 | 2015-04-13 | Yes | 2015-05-07 | 0 | 24 | 24 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77138 | 04/MRE07/35 | 31586 | NHS Permission | STAMPEDE - York | 2015-04-14 | 2015-04-14 | Yes | 2015-05-18 | 0 | 34 | 34 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77139 | 13/EM/0395 | 137840 | NHS Permission | TAGS | 2015-04-20 | 2015-04-20 | Yes | 2015-05-21 | 0 | 31 | 31 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77140 | 14/SC/1219 | 159391 | NHS Permission | AIRWAYS 2 - York | 2015-04-21 | 2015-04-28 | Yes | 2015-06-22 | 7 | 55 | 62 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77141 | 14/SC/1223 | 135378 | NHS Permission | CALIBER | 2015-05-11 | 2015-05-13 | No |  | 2 |  |  | No | [6 empty] | Please Select... | [5 empty] | Y | [5 empty] | Study on hold due to local staffing issues. | NHS Provider
77142 | 14/NE/1040 | 140698 | NHS Permission | OPAL Balance | 2015-04-14 | 2015-05-22 | Yes | 2015-06-30 | 38 | 39 | 77 | No | [6 empty] | Please Select... | [10 empty] | Y | Patients can only be recruited into this study once they have completed one of the other two OPAL studies (BEYOND and BROADEN). No patients could have been recruited into this trial before the first patient was actually recruited. | Neither
77143 | 13/WM/0419 | 134352 | NHS Permission | MAMMO 50 - York | 2015-05-27 | 2015-05-27 | Yes | 2015-07-06 | 0 | 40 | 40 | Yes | [6 empty] | Please Select... | [5 empty] | Y | [5 empty] | Study on hold due to local staffing issues. | NHS Provider
77145 | 14/NE/1214 | 162696 | NHS Permission | M14-359 (Veliparib) | 2015-06-05 | 2015-06-09 | Yes | 2015-06-19 | 4 | 10 | 14 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77146 | 15/YH/0107 | 167755 | NHS Permission | YORVIC | 2015-05-26 | 2015-06-16 | Yes | 2015-08-21 | 21 | 66 | 87 | No | [6 empty] | Please Select... |  | Y |  |  | Y |  |  |  | Y |  |  | Delay in issuing NHS permission due to resolving indemnity issue with Sponsor. | Sponsor
77147 | 15/YH/0233 | 179038 | NHS Permission | CLEARCarotid | 2015-06-22 | 2015-07-07 | Yes | 2015-08-03 | 15 | 27 | 42 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77148 | 14/YH/0076 | 141623 | NHS Permission | BALANCED | 2015-09-03 | 2015-09-03 | Yes | 2015-09-14 | 0 | 11 | 11 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77149 | 14/NI/1120 | 149397 | NHS Permission | EDNA | 2015-08-04 | 2015-08-17 | Yes | 2015-08-25 | 13 | 8 | 21 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77150 | 14/SC/1219b | 159391 | NHS Permission | AIRWAYS 2 - Scarborough | 2015-08-14 | 2015-08-14 | No |  | 0 |  |  | No | [6 empty] | Please Select... | [10 empty] | Y | Patients can only be recuited following admission by ambulance and ICU survival. Potential recruits are rare and we have no agreed local target with Sponsor. The study is open until July 2-17. Just one potential patient has presented in Scarborough who died. | Neither
77152 | 13/SS/0081 | 128254 | NHS Permission | TWICS | 2015-07-22 | 2015-08-25 | No |  | 34 |  |  | No | [6 empty] | Please Select... | [7 empty] | Y |  |  | Y | Recruitment proving challenging as patients existing medication is a factor as well as other medical problems due to the drug involved. Currently looking to open local PIC sites (GP practices) to aid recruitment. | NHS Provider
77153 | 14/EM/1173 | 162392 | NHS Permission | HI-Light Vitiligo Trial | 2015-07-09 | 2015-07-31 | Yes | 2015-08-18 | 22 | 18 | 40 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77154 | 12/WM/0335 | 97743 | NHS Permission | OCS-Care | 2015-09-02 | 2015-09-02 | Yes | 2015-09-24 | 0 | 22 | 22 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77155 | 15/LO/0992 | 173319 | NHS Permission | Proactive Health Coaching in the English NHS | 2015-07-31 | 2015-07-31 | Yes | 2015-08-17 | 0 | 17 | 17 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77156 | 14/WA/1075 | 150715 | NHS Permission | Headpost | 2015-09-22 | 2015-09-22 | Yes | 2015-09-28 | 0 | 6 | 6 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77157 | 14/LO/0203 | 137863 | NHS Permission | CLARITY | 2015-06-10 | 2015-06-11 | Yes | 2015-07-03 | 1 | 22 | 23 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77158 | 13/YH/0229 | 125373 | NHS Permission | GO2 Version 1.0 - Scarborough | 2015-06-09 | 2015-07-01 | Yes | 2015-08-06 | 22 | 36 | 58 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77159 | 14/SC/1425 | 159287 | NHS Permission | SPECTRI | 2015-06-24 | 2015-07-08 | Yes | 2015-08-28 | 14 | 51 | 65 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77160 | 15/YH/0235 | 168009 | NHS Permission | IMPACCT | 2015-10-13 | 2015-10-13 | Yes | 2015-11-09 | 0 | 27 | 27 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77161 | 15/SC/0287 | 173772 | NHS Permission | Provision of Psychological support to People in Intensive Care (v1.0) - POPPI | 2015-10-16 | 2015-10-16 | Yes | 2015-11-06 | 0 | 21 | 21 | Yes | [6 empty] | Please Select... | [12 empty] | Please Select...
77162 | 14/SC/0171 | 120104 | NHS Permission | Add-Aspirin | 2015-11-11 | 2015-12-29 | Yes | 2016-03-07 | 48 | 69 | 117 | No | [6 empty] | Please Select... | [11 empty] | No eligible participants due to eligibility criteria | NHS Provider
77163 | 13/EM/0348 | 122371 | NHS Permission | Monoprost compared to Lumigan in POA glaucoma/ocular hypertension | 2015-06-16 | 2015-11-02 | No |  | 139 |  |  | No | [6 empty] | Please Select... |  |  |  |  | Y | Y | [5 empty] | Delay in green lighting study locally mainly caused by delayed receipt of drug from sponsor. Also a delay in getting confirmation of a second investigator at site. | Both
77164 | 14/NW/0277 | 121660 | NHS Permission | BreatheMOR-HF: Morphine for breathlessness in heart failure | 2015-11-11 | 2015-11-27 | Yes | 2016-02-04 | 16 | 69 | 85 | No | [6 empty] | Please Select... | [11 empty] | Participants failed to recruit | NHS Provider
77165 | 10/H0802/46 | 52863 | NHS Permission | REVIVED-BCIS2 Version 1.0 | 2015-11-10 | 2015-11-12 | No |  | 2 |  |  | No | [6 empty] | Please Select... | [11 empty] | Eligibility criteria | NHS Provider
79200 | 14/YH/1259 | 163195 | NHS Permission | ALPHA | 2016-01-22 | 2016-02-19 | No |  | 28 |  |  | Within 70 Days | [6 empty] | Please Select... | [12 empty] | Please Select...
79201 | 15/LO/1166 | 178877 | NHS Permission | HARRIER RTH 258 | 2016-01-20 | 2016-02-19 | No |  | 30 |  |  | No | [6 empty] | Please Select... | [11 empty] | Sponsor met global target and closed study | Sponsor
79203 | 15/EE/00/10 | 138590 | NHS Permission | PITCHES | 2016-03-21 | 2016-03-31 | No |  | 10 |  |  | Within 70 Days | [6 empty] | Please Select... | [12 empty] | Please Select...