## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
84384 | 16/EM/0186 | 173279 | C&C | STAR TREC |  | Yes | 2018-10-04 |  |  | 04/04/2017 | 04/04/2017 | 2018-04-17 | 2016-10-31 | 17/05/2018 | 17/05/2018 |  | 17/05/2018 |  |  |  | Y |  | Y |  |  |  |  | Delays with return of contract from Sponsor. No eligible patients seen | Sponsor & NHS Provider
104874 | 18/LO/0141 | 233922 | C&C | OPINION |  | Yes | 2019-01-25 |  |  | 2018-03-23 | 2018-04-16 | 2018-06-04 | 2018-03-23 | 2018-05-29 | 2018-06-04 |  | 2018-06-13 | [5 empty] | Y |  |  | Y | Y | BRCA testing not requested early enough as part of SC in the NHS nationally - and slow turnaround time when is - failing nationally - sponsor looking at steps to independently provide BRCA testing during screening | Neither
106450 | 18/LO/1311 | 248599 | C&C | RHINE |  | No |  |  |  |  | 24/05/2018 | 2018-10-17 | 2018-07-05 | 2018-11-20 | 2018-11-16 |  | 2018-11-20 | [6 empty] | Y |  |  |  | A present potential first patient still going through screening period.
88025 | 17/SS/0082 | 222441 | C&C | So-START |  | No |  |  |  |  | 17/09/2018 | 2018-11-06 | 2017-07-05 | 15/11/2018 | 2018-11-09 |  | 2018-11-23 | [5 empty] | Y |  | Y |  |  | No eligible patients seen in clinic. | Sponsor & NHS provider
32880 | 17/LO/0082 | 217324 | C&C | PURASTAT |  | Yes | 2018-07-30 |  |  |  | 2018-01-17 | 2018-06-12 | 2018-03-15 | 2018-07-06 | 2018-07-17 |  | 2018-07-26
103202 | 18/NE/0296 | 248487 | C&C | CALIBRE |  | Yes | 2019-02-20 | 2019-02-01 |  |  | 2018-10-26 | 2019-01-11 | 2018-10-19 | 2019-02-01 | 2019-01-21 |  | 2019-02-01
109049 | 18/EM/0298 | 251419 |  | TRCA-303, VALOR CKD |  | No |  |  |  |  | 2018-04-23 | 2018-11-28 | 2018-11-21 | 2019-01-28 | 2019-01-28 | [5 empty] | Y |  | Y |  |  |  |  | Delays due to training not being provided swiftly by Sponsor including accesses to EDC and trainign portal. Pre-screening many patients but few eligible. | Sponsor & NHS provider
99550 | 18/NE/0194 | 242874 |  | SOLOIST |  | Yes | 2019-04-04 |  |  |  | 2018-06-05 | 2019-02-05 | 2018-08-13 | 2018-12-18 | 2019-02-11 |  | 2019-02-12

## Sheet2
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10
2018-03-11
2018-03-12
2018-03-13
2018-03-14
2018-03-15
2018-03-16
2018-03-17
2018-03-18
2018-03-19
2018-03-20
2018-03-21
2018-03-22
2018-03-23
2018-03-24
2018-03-25
2018-03-26
2018-03-27
2018-03-28
2018-03-29
2018-03-30
2018-03-31
2018-04-01
2018-04-02
2018-04-03
2018-04-04
2018-04-05
2018-04-06
2018-04-07
2018-04-08
2018-04-09
2018-04-10
2018-04-11
2018-04-12
2018-04-13
2018-04-14
2018-04-15
2018-04-16
2018-04-17
2018-04-18
2018-04-19
2018-04-20
2018-04-21
2018-04-22
2018-04-23
2018-04-24
2018-04-25
2018-04-26
2018-04-27
2018-04-28
2018-04-29
2018-04-30
2018-05-01
2018-05-02
2018-05-03
2018-05-04
2018-05-05
2018-05-06
2018-05-07
2018-05-08
2018-05-09
2018-05-10
2018-05-11
2018-05-12
2018-05-13
2018-05-14
2018-05-15
2018-05-16
2018-05-17
2018-05-18
2018-05-19
2018-05-20
2018-05-21
2018-05-22
2018-05-23
2018-05-24
2018-05-25
2018-05-26
2018-05-27
2018-05-28
2018-05-29
2018-05-30

## Sheet3
2017-05-08
2017-05-09
2017-05-10
2017-05-11
2017-05-12
2017-05-13
2017-05-14
2017-05-15
2017-05-16
2017-05-17
2017-05-18
2017-05-19
2017-05-20
2017-05-21
2017-05-22
2017-05-23
2017-05-24
2017-05-25
2017-05-26
2017-05-27
2017-05-28
2017-05-29
2017-05-30
2017-05-31
2017-06-01
2017-06-02
2017-06-03
2017-06-04
2017-06-05
2017-06-06
2017-06-07
2017-06-08
2017-06-09
2017-06-10
2017-06-11
2017-06-12
2017-06-13
2017-06-14
2017-06-15
2017-06-16
2017-06-17
2017-06-18
2017-06-19
2017-06-20
2017-06-21
2017-06-22
2017-06-23
2017-06-24
2017-06-25
2017-06-26
2017-06-27
2017-06-28
2017-06-29
2017-06-30
2017-07-01
2017-07-02
2017-07-03
2017-07-04
2017-07-05
2017-07-06
2017-07-07
2017-07-08
2017-07-09
2017-07-10
2017-07-11
2017-07-12
2017-07-13
2017-07-14
2017-07-15
2017-07-16
2017-07-17
2017-07-18
2017-07-19
2017-07-20
2017-07-21
2017-07-22
2017-07-23
2017-07-24
2017-07-25
2017-07-26
2017-07-27
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
2017-08-04
2017-08-05
2017-08-06
2017-08-07
2017-08-08
2017-08-09
2017-08-10
2017-08-11
2017-08-12
2017-08-13
2017-08-14
2017-08-15
2017-08-16
2017-08-17
2017-08-18
2017-08-19
2017-08-20
2017-08-21
2017-08-22
2017-08-23
2017-08-24
2017-08-25
2017-08-26
2017-08-27
2017-08-28
2017-08-29
2017-08-30
2017-08-31
2017-09-01
2017-09-02
2017-09-03
2017-09-04
2017-09-05
2017-09-06
2017-09-07
2017-09-08
2017-09-09
2017-09-10
2017-09-11
2017-09-12
2017-09-13
2017-09-14
2017-09-15
2017-09-16
2017-09-17
2017-09-18
2017-09-19
2017-09-20
2017-09-21
2017-09-22
2017-09-23
2017-09-24
2017-09-25
2017-09-26
2017-09-27
2017-09-28
2017-09-29
2017-09-30
2017-10-01
2017-10-02
2017-10-03
2017-10-04
2017-10-05
2017-10-06
2017-10-07
2017-10-08
2017-10-09
2017-10-10
2017-10-11
2017-10-12
2017-10-13
2017-10-14
2017-10-15
2017-10-16
2017-10-17
2017-10-18
2017-10-19
2017-10-20
2017-10-21
2017-10-22
2017-10-23
2017-10-24
2017-10-25
2017-10-26
2017-10-27
2017-10-28
2017-10-29
2017-10-30
2017-10-31
2017-11-01
2017-11-02
2017-11-03
2017-11-04
2017-11-05
2017-11-06
2017-11-07
2017-11-08
2017-11-09
2017-11-10
2017-11-11
2017-11-12
2017-11-13
2017-11-14
2017-11-15
2017-11-16
2017-11-17
2017-11-18
2017-11-19
2017-11-20
2017-11-21
2017-11-22
2017-11-23
2017-11-24
2017-11-25
2017-11-26
2017-11-27
2017-11-28
2017-11-29
2017-11-30
2017-12-01
2017-12-02
2017-12-03
2017-12-04
2017-12-05
2017-12-06
2017-12-07
2017-12-08
2017-12-09
2017-12-10
2017-12-11
2017-12-12
2017-12-13
2017-12-14
2017-12-15
2017-12-16
2017-12-17
2017-12-18
2017-12-19
2017-12-20
2017-12-21
2017-12-22
2017-12-23
2017-12-24
2017-12-25
2017-12-26
2017-12-27
2017-12-28
2017-12-29
2017-12-30
2017-12-31
2018-01-01
2018-01-02
2018-01-03
2018-01-04
2018-01-05
2018-01-06
2018-01-07
2018-01-08
2018-01-09
2018-01-10
2018-01-11
2018-01-12
2018-01-13
2018-01-14
2018-01-15
2018-01-16
2018-01-17
2018-01-18
2018-01-19
2018-01-20
2018-01-21
2018-01-22
2018-01-23
2018-01-24
2018-01-25
2018-01-26
2018-01-27
2018-01-28
2018-01-29
2018-01-30
2018-01-31
2018-02-01
2018-02-02
2018-02-03
2018-02-04
2018-02-05
2018-02-06
2018-02-07
2018-02-08
2018-02-09
2018-02-10
2018-02-11
2018-02-12
2018-02-13
2018-02-14
2018-02-15
2018-02-16
2018-02-17
2018-02-18
2018-02-19
2018-02-20
2018-02-21
2018-02-22
2018-02-23
2018-02-24
2018-02-25
2018-02-26
2018-02-27
2018-02-28
2018-03-01
2018-03-02
2018-03-03
2018-03-04
2018-03-05
2018-03-06
2018-03-07
2018-03-08
2018-03-09
2018-03-10