## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Submission Type | Name of Trial | Date of NHS Permission | First Patient Recruited? | Date of First Patient Recruited | Duration between VRA and NHS Permission | Duration between NHS Permission and First Patient | Date Study Initiated | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | A - Permissions delayed/denied | B - Suspended by sponsor | C - Closed by sponsor | D - Sponsor Delays | E - Staff availability issues | F - No patients seen | G - No patients consented | H - Contracting delays | I - Rare diseases | J - Other | Comments | Reasons for delay correspond to:
103202 | 18/NE/0296 | 248487 | C&C | CALIBRE |  | Yes | 2019-02-20 | 2019-02-01 |  |  | 2018-10-26 | 2019-01-11 | 2018-10-19 | 2019-02-01 | 2019-01-21 |  | 2019-02-01
99550 | 18/NE/0194 | 242874 |  | SOLOIST |  | Yes | 2019-04-04 |  |  |  | 2018-06-05 | 2019-02-05 | 2018-08-13 | 2018-12-18 | 2019-02-11 |  | 2019-02-12
114058 | 19/EM/0047 | 257111 |  | TENAYA |  | Yes | 2019-08-02 |  |  |  | 05/11/2018 | 2019-04-05 | 2019-04-04 | 2019-06-05 | 2019-06-04 |  | 2019-06-05
89791 | 18/LO/0165 | 224726 |  | POLEM |  | No |  |  |  |  | 2018-10-30 | 2019-02-20 | 2019-02-20 | 20/02/2019 | 20/05/2019 |  | 2019-05-31 |  |  |  | Y | [5 empty] | Y | Sponsor delays in submitting HRA Approval fro site. Pharmacy delays with authorising chemotherapy regime | Sponsor & NHS provider
107542 | 18/LO/0710 | 245369 |  | POLAR A |  | No |  |  |  |  | 2018-01-11 | 2019-03-05 | 2018-08-31 | 2019-06-04 | 2019-05-30 |  | 2019-06-04 | [9 empty] | Y | Pharmacy delays with authorising chemotherapy regime | NHS provider
106875 | 18/LO/0645 | 239233 |  | POLAR M |  | Yes | 2019-06-18 |  |  |  | 2018-01-11 | 2019-03-05 | 2018-08-31 | 2019-06-04 | 2019-05-30 |  | 2019-06-04 | [9 empty] | Y | Pharmacy delays with authorising chemotherapy regime | NHS provider
94281 | 18/SS/0033 | 242190 |  | BICs |  | Yes | 2019-06-27 |  |  |  | 2018-08-09 | 2019-04-17 | 2018-08-09 | 2019-05-24 | 2019-05-13 |  | 2019-05-24
| 19/SW/0070 | 259679 |  | CAPITELLO-290 |  | Yes | 2019-09-17 |  |  |  | 30/05/2019 | 2019-05-30 | 2019-05-02 | 2019-08-02 | 2019-08-15 |  | 2019-08-15
108574 | 18/SC/0243 | 240684 |  | ORION4 |  | Yes | 2019-09-11 |  |  |  | 2018-03-07 | 2019-04-02 | 2018-10-01 | 2019-07-12 | 2019-09-06 |  | 2019-09-06
39163 | 18/NW/0695 | 244971 | C&C | OAKS |  | No |  |  |  |  | 2018-06-19 | 2019-06-27 | 2018-08-10 | 2019-12-19 | 18/12/2019 |  | 08/01/2020 | [6 empty] | Y |  |  |  | Screening of 1st patient still ongoing, 30 day duration
37407 | 19/LO/0253 | 257127 | C&C | CA017-078 |  | No |  |  |  |  | 2018-11-23 | 08/10/2019 | 2019-03-27 | 02/12/2019 | 2019-12-09 |  | 09/12/2019 | [6 empty] | Y |  |  |  | No eligible patients seen as yet
112731 | 18/SC/0454 | 249509 |  | POISE 3 |  | No |  |  |  |  | 2018-08-03 | 2019-02-05 | 2019-01-16 | 2019-12-03 | 2019-12-03 |  | 2019-12-06 |  |  |  | Y |  |  | Y | Y |  |  | Sponsor used non model agreement. This made contracting very challenging. Set up was paused until this was resolved. Pharamcy timeline took longer than planned. | Sponsor & NHS provider
104950 | 18/LO/1290 | 249002 |  | Hookipa H-100-002 |  | No |  |  |  |  | 2019-04-16 | 2019-05-27 | 2018-11-06 | 2019-07-17 | 2019-07-22 |  | 2019-10-16 | [5 empty] | Y | Y |  |  | Y | Very difficult to get the right match of patients e.g. donar to recipent that match on lab work to be eligible. Due to GMO status and our site been new to this type of study we were required to gain extra approvals via HSE. Training delays. | Sponsor & NHS provider