Equality Objectives 2012 – 2016

In compliance with the Equality Act 2010

Updated July 2015

Content

| Page |  |
| --- | --- |
| 1 | Content |
| 2 | Introduction |
| 3 | The Equality Delivery System |
| 4 | Adopting the Equality Delivery System |
| 5 | Developing and monitoring our equality objectives |
| 6 | Objective 1 |
| 7 | Objective 1 |
| 8 | Objective 2 |
| 9 | Objective 3 |
| 10 | Objective 4 |
| 11 | Objective 4 |
| 12 | How to obtain this information in a different language or format |

Introduction

York Teaching Hospital NHS Foundation Trust is committed to promoting equality, diversity and human rights in its day to day treatment of all patients, visitors and staff regardless of age, disability, race, ethnic origin, gender, gender identity, marital status, religion or belief or sexual orientation.

Our mission is:

“To be trusted to deliver safe, effective and sustainable healthcare within our communities”

Our values, drivers and motivators to achieve this are:

- Caring about what we do

- Respecting and valuing each other

- Listening in order to improve

- Always doing what we can to be helpful

How we promote safe and effective healthcare for all who need it and work to provide it is outlined in “our shared commitment” which is published on our website.

This document explains the need for the Trust to set equality objectives, how we develop these and our progress to date.

The Equality Delivery System (EDS)

The Equality Delivery System (EDS) was originally a product of the Department of Health Equality and Diversity Council (EDC) designed to help NHS organisations, in discussion with local partners to review and improve performance and help to meet their statutory and regulatory obligations for equality, diversity and human rights.

York Teaching Hospital NHS Foundation Trust held our first grading day in March 2012 which included the development of our equality objectives. Nationally in 2012 the implementation of the EDS was independently evaluated and subsequent consultation with NHS organisations developed a refreshed EDS called EDS2 that was launched in November 2013 allowing more flexibility for local implementation.

EDS2 has 4 goals and 18 outcomes, with enough in common between the original and EDS2 for meaningful comparisons to be made over time.

- Better health outcomes for all

- Improved patient access and experience

- A representative and supported workforce

- Inclusive leadership

These outcomes focus on the issues of most concern to patients, carers, communities, NHS staff and Boards. It is against these outcomes that performance is graded and action determined.

Adoption of the EDS

In November 2011 to drive up equality performance and embed it into mainstream / core business York Teaching Hospital NHS Foundation Trust adopted the EDS.

It also helps us to meet:

- the requirements of the public sector Equality Duty

- equality aspects of the NHS Constitution

- equality aspects of the NHS Outcomes Framework

- equality aspects of CQC's Essential Standards

In March 2012 we held a grading day which included development of our equality objectives.

During 2014 those with responsibility for equality and diversity at York Teaching Hospital Foundation Trust, Leeds York Partnership Foundation Trust and Vale of York Clinical commissioning Group (CCG) agreed to work together with community representatives to make best use of time and resources and carry out EDS2 collaboratively and begin working towards joint objectives.

Stakeholders were invited to a planning meeting to discuss a preferred approach to EDS2, how they wanted to be involved and how the assessment and grading would be carried out with representation from each of the protected characteristics. The stakeholders approved this new way of working and agreed there should be a focus on just one goal (Improved patient access and experience) to enable time for meaningful discussion and assessment.

Each organisation compiled evidence which was distributed prior to an assessment and grading event 24th March 2015. The summary report for each organisation is published on respective websites as required by NHS England.

Developing Our Objectives

Our objectives were first developed by the EDS grading panel March 2012.  In March 2015 at the assessment and grading event mentioned above joint equality priorities were agreed and these have been added to our equality objective action plan. The overall objectives remain the same with actions amended; removing those completing and adding the new priorities.

We have four objectives:

- Improve data collection, analysis and monitoring for protected characteristics

- Further develop engagement and involvement of patients, carers, governors and staff to reflect local demographics

- Develop strong partnerships with social care and GP’s to ensure patient pathways are free from barriers between providers for everyone

- Continue with staff development programme ensuring equality and diversity is embedded into all decision making processes

Objective Action Plan

An action plan for each equality objective following the SMART principle forms the remainder of this document, progress to date is noted. Asterisk * denotes 2015 EDS2 action

Monitoring

Our objectives are monitored by the Trust Fairness Forum (formerly known as the Equality and Diversity Committee) with a progress report presented to the Board on an annual basis.

Objective 1

Improve data collection, analysis and monitoring for protected characteristics

This links to EDS goals 1, 2, 3 and 4

| Action | Responsible Director | Target Date | Measures | Progress |
| --- | --- | --- | --- | --- |
| 1.1 | Ensure data from surveys and feedback is capable of analysis by protected characteristic | S Rushbrook S Holden | 31/12/15 | Explore current exceptions on data sets + action plan Increased completion and return rates of monitoring information | Gaps identified Discussions ongoing with Systems and Network Services(SNS) to ensure capture of protected characteristics |
| 1.2 | Review approaches to data collection and Datix system for PET and PALS to ensure ability to disaggregate comments / complaints to protected characteristics | B Geary PET Lead | 31/12/15 | Improve response rate for complaint monitoring form. Production of evidence based trends/themes | New monitoring form implemented though return rates are low – review including how to raise awareness underway |
| 1.3 | Raise awareness to the importance of recording protected characteristics where appropriate: Patients Staff | B Geary S Holden | On going | Decreases in number of prefer not to say responses. | Included in corporate induction, awareness events throughout the year |
| 1.4 | Disaggregate performance indicators by protected characteristic and analyse outcomes of different PC's to set objectives | J Walters L Turner | 31.12.15 | 18 week admitted breaches, DNA's, ED and cancer breaches, | Please see 1.1 and 1.4 |
| 1.5 | Review options for monitoring of patients using CPD including capturing patient protected characteristics and specific requirements | S Rushbrook A Lee | 31/12/15 | All protected characteristics captured and compliance with Information standard ISB 1605 | Please see 1.1 |
| * 1.6 | Investigate establishment of a central information hub including monitoring and review process | S Holden M Milburn | 31/09/15 | Feedback from policy writers and individuals who complete equality analysis Picture bank of inclusive images | Work in progress - to be developed |

| Action | Responsible Director | Target Date | Measures | Progress |
| --- | --- | --- | --- | --- |
| 1.7 | Work force data - Monitor job applicant conversion rates | S Holden S Longhorne | 31/12/15 | Analysis of job application conversion rates to be included in annual Equality in Our Workforce Report | Conversion rates included in 2013-2014 Equality, diversity and human rights report |
| 1.8 | Workforce data - Monitor development programme applications and progression for Band 4&5 | S Holden S Wild | 31/04/15 On going | Personal training data capture on Learning Hub Quarterly report to Education Review Board Link to HR data re recruitment/ progression of staff to higher roles | Learning hub now live – data will be available for 2014/2015 |
| * 1.9 | Improve collection and analysis of patient/service user data with focus on sexual orientation and age | S Rushbrook S Holden A Lee M Milburn | 31/03/16 | Improve response rate Decreases in number of prefer not to say responses. | Links to 1.1 -1.6 inclusive |
| * 1.10 | Review current processes to raise concerns, make a complaint or to access PALS support including use of technology to enable greater access | B Geary New PET lead | 31/03/16 |  |  |

Objective 2

Further develop engagement and involvement of patients, carers, governors and staff to reflect local demographics

This links to EDS2 goals 1, 2, 3 and 4

| Action | Responsible Director | Target Date | Measures | Progress |
| --- | --- | --- | --- | --- |
| 2.1 | Complete a mapping exercise to identify gaps and develop a plan to ensure we include people with protected characteristics (PC’s) reflecting local demographics with focus on specific groups e.g LGBT(Lesbian, Gay, Bi-sexual and Transgender) and gypsies and travellers | S Holden M Milburn | 30/09/15 | Define demographics of Trust area List of current Trust connections Action plan to address areas where PC’s are not engaged/involved/ do not reflect local demographics | Links to 1.6 |
| 2.2 | Ensure corporate communications and engagement strategy supports Equality and Diversity objectives | P Crowley L Brown | 30/06/15 | Report on performance to the Board of Directors at agreed intervals | Discussions re Communications strategy in progress |
| 2.3 | Capture qualitative data and develop case studies to share experiences and enable learning | B Geary New PET lead | On going | Defined capture process Bank of case studies available for staff | Patient stories captured on naturally occurring basis |

Objective 3

Develop strong partnerships with social care and GP’s to ensure patient pathways are free from barriers between providers for everyone

This links to EDS2 goal 1and 2

| Action | Responsible Director | Target Date | Measures | Progress |
| --- | --- | --- | --- | --- |
| 3.1 | Continue EDS2 grading collaboratively with other health care providers | S Holden M Milburn | 31/03/15 | Representative Grading Panel + inclusive of the area the Trust covers | Goal 2 assessed March 2015 Other goals to follow |
| 3.2 | Review capture of protected characteristics at point of patient entry | S Holden S Rushbrook A Lee |  | Electronic capture Compliance with Information standard ISB 1605 | Develop plan with systems and network to ensure protected characteristics are included as mandatory fields on CPD |
| 3.3 | Review availability of this capture across pathways | S Rushbrook A Lee |  |  | Links to 1.1 and 1.5 |
| 3.4 | Improve access to services: |  |  |  |  |
| * 3.4.1 | Review outpatient appointment system / choose and book. To include first point of contact processes and consideration of options to increase choice for service users | S Rushbrook A Lee |  |  |  |
| 3.4.2 | Develop access audit tool | B Golding | 31/12/15 |  | In progress to link with Access to Services Group |
| * 3.5 | Review first point of contact processes and to develop and promote alternative contact processes where appropriate e.g text message | S Rushbrook A Lee | 31/03/15 | Increased options Improved access to our services |  |

Objective 4

Continue with staff development programme ensuring equality and diversity is embedded into all decision making processes

This links to EDS2 goal 4

| Action | Responsible Director | Target Date | Measures | Progress |
| --- | --- | --- | --- | --- |
| 4.1 | Review how data feeds into the Trust Business Cycle | ? M Proctor |  |  |  |
| 4.2 | Produce evidence of debate related to inclusivity at Board of Directors | P Crowley A Pridmore | ¼ly and on going | Corporate risk register and assurance framework presented to the Board Completion of paper front pages Standard Operating Procedure for Corporate Governance Review minutes |  |
| 4.3 | Review advertising practice for development programmes and monitor applicant conversion and progression for band 4&5 | S Holden W Thornton | 31/04/15 on going | Review training opportunities at band 5. | Learning hub now live – data will be available for 2014/2015 need to link to HR/ESR change forms |
| 4.4 | Review equality analysis process and documentation | S Holden M Milburn L Larcum | 31/12/15 | New style equality analysis introduced by relevance and then rolling programme Centralise monitoring | In progress |
| 4.5 | Develop a champion role | S Holden M Milburn | On going | Contacts monitored Champions spread | Complete First group trained and introduced September 2014 |
| * 4.6 | Develop and implement a joint approach to equality and diversity training | S Holden M Milburn | 31/03/16 | Uptake monitored via Learning Hub |  |
| Action | Responsible Director | Target Date | Measures | Progress |
| * 4.7 | Develop training so that staff feel comfortable to ask questions related to protected characteristics | S Holden M Milburn | 31/03/16 | Uptake monitored via Learning Hub Improved level of recording protected characteristics | Potential link to 4.6 |