## Progress (reporting)
Medical Pay Gap Action Plan - April 2025 |  |  |  |  | Appendix 2
FOR REPORTING: Reporting template (RAG Ratings)
Action | Sub-Actions | Responsible | Target date | Narrative | Progress
3 Improvement plan to eliminate pay gaps | 3.1 Implement the Mend the Gap review recommendations for medical staff and develop a plan to apply those recommendations to senior non-medical workforce (by March 2024) |  |  | Mend the Gap Review recommendations as outlined https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/944246/Gender_pay_gap_in_medicine_review.pdf where Trusts are responsible for implementation (where achievable)
| 3.2 Further analysis of the EPG for the Trust’s Medical and Dental workforce by the Medical Workforce team. |  |  | Model recruitment process as described by https://nhsproviders.org/race-equality-what-works-resource/10-steps-a-model-recruitment-process
Mend the Gap recommendations
Make senior jobs more accessible to women | 3.1.1 Employers should promote a flexible working culture when advertising jobs. They should make clear that reduced hours, flexible working and job-share opportunities are available (unless strong, justifiable reasons exist and are documented for not offering them). They should publish details of their flexible working and job-share policies on their website for all potential employees to access | Recruitment team | 2025-07-01 | To better understand the impact of this action, the current percentage of women in senior medical roles will be obtained and measured against the following years data. Flexible working options published alongside every medical advert where possible. | Complete
| 3.1.2 Promote flexible working to appeal more to men to increase the percentage of men that work LTFT, encouraging more equal sharing of caring responsibilities, reducing the stigma for men and, reducing the number of women obliged to choose LTFT working to accommodate caring responsibilities, particularly in primary care | Recruitment team and Management teams | 2026-02-01 | To better understand the impact of this action, information will be gathered to understand those already undertaking a flexible working arrangement across the various grades. This will then be measured during the next pay gap reporting round to identify whether a positive increase is identified. | On-going. Between Aug 24- Aug 25, of the 430 trainees recruited, 117 joined LTFT. The percentage breakdown is 32% males and 68% females. This includes Trust grade posts.
Introduce increased transparency on gender pay gaps | 3.1.3 Increase the use of national pay contracts in place of local pay arrangements for hospital doctors | Employment team/Recruitment/Rob Newton/SAS Advocates/Sarah Crossland (Ops rep) | 2026-02-01 | On-going work to move away from Associate Specialist contract as this is frequently used when recruiting from overseas. Career pathway discussions are on-going to enable progression from Specialty Doctor to Specialist. | On-going. Transition guidance shared with LNC. Data gathering exercise to be undertaken to understand current picture of the AS workforce
| 3.1.4 As far as possible to use standard rates for additional paid activity that are consistent and transparent (for example, waiting list initiatives, locum work) | Deployment team and Management teams. Lydia Larcum | 2026-02-01 | Agreement for harmonisation of medical pay paper approved at Exec Committee. In relation to bank rates, the escalation process has been strengthened to remove autonomy from Care Groups. Escalations are now approved only by Exec Directors. This provides consistency in determining pay arrangements for temporary cover. | On hold whilst national negotiations regarding pay take place, given the mandate for industrial action the BMA currently have.
Mandate change to policy on gender pay gaps | 3.1.5 All candidates who meet the job description requirements will, wherever practicable, be shortlisted for senior medical jobs, clinical academic jobs and GP partnerships | Recruitment team and Management teams | 2025-07-01 | This is currently happening as standard practice within the organisation | Complete
Ethnicity Pay Gap recommendations
Job descriptions and advertising | 3.1.6 Ensuring there is a statement on reasonable adjustments and EDI priorities. | Recruitment team | 2025-05-01 | EDI statement included on new job description template | Complete
| 3.1.7 Input should be sought from employee networks for both inclusive recruitment policy and monitoring inclusive recruitment practice. | Recruitment team | 2025-09-01 | Policy reviewed with Head of EDI and ratified. Bespoke training sessions developed to be delivered to senior management to reinforce the message on inclusive recruitment | Complete
| 3.1.7 Ensure that a flexible working policy is included in the description to encourage diverse candidates. | Operational HR team/Employment team | 2025-07-01 | New candidate pack includes details on flexible working and networks. This is published alongside every advert Trust wide. | Complete
| 3.1.8 Include organisational structure and reporting lines in the description and provide candidates with the opportunity to speak to recruiting managers before applying. | Recruitment team | 2025-07-01 | Included as part of new job description and person spec template | Complete
Interview and Selection | 3.1.9 Panel members should evidence training and or awareness of inclusive recruitment and interviewing techniques. | Management teams | 2025-09-01 | This is listed on the vacancy planning form to highlight those who need training. New training developed. Sessions need to be scheduled. | On-going
Steps to a Model Recruitment Process for Race Equality
| 3.2.1 The job description and advert should be analysed for gendered and non-inclusive language before the advert goes live and inappropriate language removed. A gender decoder tool can be used for this. | Recruitment team/Management teams | 2025-07-01 | Carried out as part of the work to move old job packs onto the Trust template | Complete
| 3.2.2 A structured interview with a full set of questions for the interview and a marking framework to be provided and each candidate asked the same questions and scored based on their answers to those questions only. | Recruitment team/Medical Director | 2025-11-01 | Suggested questions have been developed and are supplied to the panel prior to conducting the interview. The questions need to be shared with REN and Enable networks to ensure the questions are inclusive | On-going
| 3.2.3 The panel to be asked to score each candidate independently without conferring with the other panellists and then submit their scores to the inclusion lead. Only then can the scores be discussed with other panellists. Panel members to be reminded of the risk of bias and to stick tightly to the structured scoring system which sets out marking criteria. | Management teams | 2025-07-01 | This happens as part of the standard practice | Complete
| 3.2.4 Scoring to be done for each candidate's answer on a scale of 1-4 based on the extent to which the candidate's answer demonstrates the desired criteria, using the marking framework provided, not against the previous candidate's answers. The importance of scoring candidate's answers against the specified criteria, not against the previous candidate's answers is stressed. | Management teams | 2025-07-01 | This happens as part of the standard practice | Complete
| 3.2.5 Each candidate will be provided with feedback on their cumulative scores for each answer as well as qualitative feedback where possible. | Management teams | 2025-07-01 | This happens as part of the standard practice | Complete

## REF HIA actions
HNY EDI Improvement Plan - HIAS quarterly reporting template
FOR REFERENCE: HIA actions by date
High Impact Action | Sub-Actions
1 EDI Objectives for Board members | 1.1 Every board and executive team member must have EDI objectives that are specific, measurable, achievable, relevant, and timebound (SMART) and be assessed against these as part of their annual appraisal process (by March 2024).
1.2 Board members should demonstrate how organisational data and lived experience have been used to improve culture (by March 2025)
1.3 NHS boards must review relevant data to establish EDI areas of concern and prioritise actions. Progress will be tracked and monitored via the Board Assurance Framework (by March 2024).
2 Inclusive Recruitment and Talent processes | 2.1 Create and implement a talent management plan to improve the diversity of executive and senior leadership teams (by June 2024) and evidence progress of implementation (by June 2025)
2.2 Implement a plan to widen recruitment opportunities within local communities, aligned to the NHS Long Term Workforce Plan. This should include the creation of career pathways into the NHS such as apprenticeship programmes and graduate management training schemes (by October 2024). Impact should be measured in terms of social mobility across the integrated care system (ICS) footprint
3 Improvement plan to eliminate pay gaps | 3.1 Implement the Mend the Gap review recommendations for medical staff and develop a plan to apply those recommendations to senior non-medical workforce (by March 2024)
3.2 Analyse data to understand pay gaps by protected characteristic and put in place an improvement plan. This will be tracked and monitored by NHS boards. Reflecting the maturity of current data sets, plans should be in place for sex and race by 2024, disability by 2025 and other protected characteristics by 2026.
3.3 Implement an effective flexible working policy including advertising flexible working options on organisations’ recruitment campaigns. (March 2024)
4 Improvement plan to address health inequalities in the workforce | 4.1 Line managers and supervisors should have regular effective wellbeing conversations with their teams, utilising resources such as the national NHS health and wellbeing framework. (by October 2023)
4.2 Work in partnership with community organisations, facilitated by ICBs working with NHS organisations and arm’s length bodies, such as the NHS Race and Health Observatory. For example, local educational and voluntary sector partners can support social mobility and improve employment opportunities across healthcare (by April 2025)
5 Induction on-boarding and development for internationally-recruited | 5.1 Before they join, ensure international recruits receive clear communication, guidance and support around their conditions of employment ; including clear guidance on latest Home Office immigration policy, conditions for accompanying family members, financial commitment and future career options (by March 2024)
5.2 Create comprehensive onboarding programmes for international recruits, drawing on best practice. The effectiveness of the welcome, pastoral support and induction can be measured rom, for example, turnover, staff survey results and cohort feedback (by March 2024)
5.3 Line managers and teams who welcome international recruits must maintain their own cultural awareness to create inclusive team cultures that embed psychological safety (by March 2024).
5.4 Give international recruits access to the same development opportunities as the wider workforce. Line managers must proactively support their teams, particularly international staff, to access training and development opportunities. They should ensure that personal development plans focus on fulfilling potential and opportunities for career progression (by March 2024)
6 Eliminate bullying discrimination harassment and bullying | 6.1 Review data by protected characteristic on bullying, harassment, discrimination and violence. Reduction targets must be set (by March 2024) and plans implemented to improve staff experience year-on-year
6.2 Review disciplinary and employee relations processes. This may involve obtaining insights on themes and trends from trust solicitors. There should be assurances that all staff who enter into formal processes are treated with compassion, equity and fairness, irrespective of any protected characteristics. Where the data shows inconsistency in approach, immediate steps must be taken to improve this (by March 2024).
6.3 Ensure safe and effective policies and processes are in place to support staff affected by domestic abuse and sexual violence (DASV). Support should be available for those who need it, and staff should know how to access it. (By June 2024)
6.4 Create an environment where staff feel able to speak up and raise concerns, with steady year-on-year improvements. Boards should review this by protected characteristic and take steps to ensure parity for all staff (by March 2024)
6.5 Provide comprehensive psychological support for all individuals who report that they have been a victim of bullying, harassment, discrimination or violence (by March 2024).
6.6 Have mechanisms to ensure staff who raise concerns are protected by their organisation.